## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Color
` | PDW ON LINE COURSE: ACTION PLAN
| Property Development Workshops |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Site Acquisition & DA Approval
|  | 2022-08-18 |  |  |  | August | [13 empty] | September | [34 empty] | October
| Scrolling Increment: | 0 | time axis 2022-08-18 to 2022-10-12
| Milestone description | Category | Progress | Start | Days | time axis 2022-08-18 to 2022-10-12
Sourcing Sites
| Complete PDW On Line Course | Milestone | 100% | 2022-08-18 | 0
| Select Council Area/LGA | Goal | 0% | 2022-08-18 | 10 | 2022-08-18: 2; 2022-08-19: 2; 2022-08-20: 2; 2022-08-21: 2; 2022-08-22: 2; 2022-08-23: 2; 2022-08-24: 2; 2022-08-25: 2; 2022-08-26: 2; 2022-08-27: 2
| Review Planning Maps for B4 R4 and R3 Zonings | Goal | 0% | 2022-08-18 | 20 | 2022-08-18: 2; 2022-08-19: 2; 2022-08-20: 2; 2022-08-21: 2; 2022-08-22: 2; 2022-08-23: 2; 2022-08-24: 2; 2022-08-25: 2; 2022-08-26: 2; 2022-08-27: 2; 2022-08-28: 2; 2022-08-29: 2; 2022-08-30: 2; 2022-08-31: 2; 2022-09-01: 2; 2022-09-02: 2; 2022-09-03: 2; 2022-09-04: 2; 2022-09-05: 2; 2022-09-06: 2
| Select Sites or create sites utilising Six Maps or Mecone | Goal | 0% | 2022-08-18 | 20 | 2022-08-18: 2; 2022-08-19: 2; 2022-08-20: 2; 2022-08-21: 2; 2022-08-22: 2; 2022-08-23: 2; 2022-08-24: 2; 2022-08-25: 2; 2022-08-26: 2; 2022-08-27: 2; 2022-08-28: 2; 2022-08-29: 2; 2022-08-30: 2; 2022-08-31: 2; 2022-09-01: 2; 2022-09-02: 2; 2022-09-03: 2; 2022-09-04: 2; 2022-09-05: 2; 2022-09-06: 2
| Check for any Site Affectations | Goal | 0% | 2022-08-18 | 20 | 2022-08-18: 2; 2022-08-19: 2; 2022-08-20: 2; 2022-08-21: 2; 2022-08-22: 2; 2022-08-23: 2; 2022-08-24: 2; 2022-08-25: 2; 2022-08-26: 2; 2022-08-27: 2; 2022-08-28: 2; 2022-08-29: 2; 2022-08-30: 2; 2022-08-31: 2; 2022-09-01: 2; 2022-09-02: 2; 2022-09-03: 2; 2022-09-04: 2; 2022-09-05: 2; 2022-09-06: 2
| Check availability on Council's DA Tacker | Goal | 0% | 2022-08-18 | 20 | 2022-08-18: 2; 2022-08-19: 2; 2022-08-20: 2; 2022-08-21: 2; 2022-08-22: 2; 2022-08-23: 2; 2022-08-24: 2; 2022-08-25: 2; 2022-08-26: 2; 2022-08-27: 2; 2022-08-28: 2; 2022-08-29: 2; 2022-08-30: 2; 2022-08-31: 2; 2022-09-01: 2; 2022-09-02: 2; 2022-09-03: 2; 2022-09-04: 2; 2022-09-05: 2; 2022-09-06: 2
| Do onsite inspection (drive by) | Goal | 0% | 2022-08-18 | 20 | 2022-08-18: 2; 2022-08-19: 2; 2022-08-20: 2; 2022-08-21: 2; 2022-08-22: 2; 2022-08-23: 2; 2022-08-24: 2; 2022-08-25: 2; 2022-08-26: 2; 2022-08-27: 2; 2022-08-28: 2; 2022-08-29: 2; 2022-08-30: 2; 2022-08-31: 2; 2022-09-01: 2; 2022-09-02: 2; 2022-09-03: 2; 2022-09-04: 2; 2022-09-05: 2; 2022-09-06: 2
| Complete Financial Feasibility/Stacks up | Milestone | 0% | 2022-08-18 | 20 | bar: 2022-08-18 to 2022-09-06
| Site Acquisition | Goal
| Prepare HoA (written offer) | Goal | 0% | 2022-09-07 | 5 | 2022-09-07: 2; 2022-09-08: 2; 2022-09-09: 2; 2022-09-10: 2; 2022-09-11: 2
| Contact Owner and make appointment to meet | Goal | 0% | 2022-09-07 | 5 | 2022-09-07: 2; 2022-09-08: 2; 2022-09-09: 2; 2022-09-10: 2; 2022-09-11: 2
| First Meeting with Owner: Fact finding | Goal | 0% | 2022-09-12 | 1 | 2022-09-12: 2
| Second Meeting: Present written offer in HOA format | Goal | 0% | 2022-09-26 | 1 | 2022-09-26: 2
| Third Meeting: Negotiate final outcome/sign HOA | Goal | 0% | 2022-09-26 | 5 | 2022-09-26: 2; 2022-09-27: 2; 2022-09-28: 2; 2022-09-29: 2; 2022-09-30: 2
| Lawyer drafts Deed of Call Ootion and prepares Contract of Sale | Goal | 0% | 2022-09-26 | 5
| Vendor's Lawyer reviews | Goal | 0% | 2022-10-10 | 5 | 2022-10-10: 2; 2022-10-11: 2; 2022-10-12: 2
| Agree on Legal Documents/Execute | Milestone | 0% | 2022-10-10 | 5
| Legal Structure | Goal
| Establish the legal structure for your property development business e.g. Unit Trust | Milestone | 0% | 2022-08-18 | 14 | bar: 2022-08-18 to 2022-08-31
| DA Approval Process | Goal
| Brief Architect & Town Planner | Goal |  | 2022-10-10 | 6 | 2022-10-10: 2; 2022-10-11: 2; 2022-10-12: 2
| Design Development | Goal |  | 2022-10-18 | 20
| Council Pre-DA Meeting | Goal |  | 2022-11-07 | 2
| Confirm Feasibility/Costs | Goal |  | 2022-11-10 | 5
| Lodge DA with Council | Goal |  | 2022-11-15 | 2
| Follow-up with Council through your Town Planner | Goal |  | 2022-11-15 | 90
| DA Approval achieved | Milestone |  | 2023-02-13 | 1
| Sales Process | Goal
To add more data, Insert new rows ABOVE this one